## Plan
Plan ID | Plan name | Date of export
az8jn0vv-0KW1WYZfNlbbMgAG46r | Week 4 - AI Travel Assistant - Team 35 ¦ A | 2026-08-16

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
Oai6-Uzh6k2ssL1x7S9GI8gAHFOF | Labels | Documents & Updates |  | Not started | Medium |  | Daniel Francisco | 2026-08-05 |  |  |  | false
qbWVqfVFrkGZG8TFCaffNMgAFeMq | [BOOTSTRAP RESTYLING] -Write requirements for team page + login styling : 60 | Done |  | In progress | Important | Wen Bin Liang | Daniel Francisco | 2026-08-05 |  |  |  | false |  |  | 5/5 | Document updated;Edge cases documented;Requirements shared with PM and UX;Team page fields listed with validation/display rules;Login scope explicitly stated as styling-only | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Update Everything on Login Restyling.docx --- Handoff note: Done: Wrote requirements for team page + login styling, including field list, scope statement, and edge cases. Deliverable:Login Restyling & Team Page Requirements Note for next role: Login is styling-only, no new/removed form fields. Team page needs 4 fields per member (name, role, photo, blurb), card-grid layout, ordered by role (PM, BA, UX, Dev). See edge cases in doc for missing photo/long blurb handling.
GilR9Pn-8EGkO9eWWTHBfsgALIXl | [BOOTSTRAP RESTYLING] Design Login Style & Team Page Layout :120 | Done |  | In progress | Medium | Ryan Lim | Daniel Francisco | 2026-08-05 |  |  |  | false |  |  | 5/5 | Visual consistency between the two checked;Login page mockup complete;Team page mockup complete;Document Updated;Design shared with BA for validation | UX;Sprint 1 | Produce a mockup/wireframe of the restyled login page and a separate mockup of the team page layout, based on the BA's requirements document. Both must be visually consistent with each other. Update Task documentTask2 (1).pdf Figma Linkhttps://www.figma.com/design/fCinxYwnsMcmcQr3c8K30E/Task2?node-id=25-18&t=eDskqq9RXL0Hc3SS-1 Handoff Done: Produced mockups for restyled login page and new team page, based on BA's requirements document. Confirmed login changes are styling only, no auth logic/field/validation changes. Deliverable: PDF file and Figma link with both mockups, visually consistent card/typography styling across login and team pages. Note for next role - BA: In the Figma link there are annotations made for Typography Styling used and Design choices.
BSmGlUxyEk6KCU8LM_9qQcgACef2 | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | Done |  | Not started | Medium | Wen Bin Liang | Daniel Francisco | 2026-08-05 |  |  |  | false |  |  | 5/5 | Every required field checked against the design;Login scope confirmed unchanged;Gaps (if any) sent back to UX and resolved;Document Updated;Design formally approved | BA;Sprint 1 | Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Update Document.docx --- Done: Reviewed Ryan's UX mockups (login + team page) against the requirements doc. Confirmed all fields present, login scope stayed styling-only, and edge cases (missing blurb, blurb truncation, missing photo) are handled in the design. Followed up with Ryan on the responsive grid reflow that the design will be implemented in the development phase. Design formally approved. Deliverable: Validate Design AgainstRequirements Note for next role: all requirements have been checked against the design and confirmed. Devs are good to proceed.
fbnP6_HU_UW3IQlkhWqaJcgAIyu7 | [BOOTSTRAP RESTYLING]- Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | Done |  | Not started | Medium | Khanh Nguyen | Daniel Francisco | 2026-08-05 |  |  |  | false |  |  | 4/4 | No authentication logic changed;Visual style matches approved mockup;Update document;Existing login validation/errors still function as before | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. update Document.docx commit: https://github.com/khanhngu-git/Group35-Team_Page/commit/fa8df233d6bf8452de1dbe9b3cbb1d77db26d943 Handoff Done: Implemented the restyled login page based on UX's approved mockups (Task2-UX.pdf). Font, background gradient, card styling, centered labels, and error banner now match the design. Confirmed changes are styling-only — no auth logic, validation, or session handling was modified, aside from one small addition noted below. Deliverable: feature/login-page branch, PR open into main on Group35-Team_Page. Note for next role — Dev (testing): Sign-up page still uses the old (unstyled) light-mode layout, so it'll look inconsistent next to the restyled sign-in page until a follow-up pass is done. Google sign-in button state (grayed out, "Signing in…") only triggers during email/password submission currently, not during the Google OAuth flow itself — worth confirming if that's intended.
MuQZJlZRuUqGXgw7xKmIvMgANTzH | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | Done |  | Not started | Medium | Khanh Nguyen | Daniel Francisco | 2026-08-05 |  |  |  | false |  |  | 4/4 | Team page renders per design with all required fields;Document updated;Team page not directly accessible without login;Successful login redirects to team page | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Update Doc commit: https://github.com/khanhngu-git/Group35-Team_Page/commit/e1239dcbb01b3bec61e6dc793e7d0e511e23b5b7Handoff Done: Built the Team page per the approved design — each member card shows name, role badge, and blurb (where provided). Added "Team" to the sidebar navigation. Wired successful login (both email/password and Google sign-in) to redirect the user to /team. Confirmed the page is unreachable without a valid session. Deliverable: feature/team-page branch, PR open into main on Group35-Team_Page. Note for next role — Dev (testing): Route protection: /team lives inside the (dashboard) route group, so it inherits the same server-side session check as /dashboard, /profile, /settings (redirects to /auth/signin if no session) — also added to proxy.ts's PROTECTED_ROUTES for the edge-level check. Please verify directly: visiting /team while logged out (or with an expired/cleared session cookie) should bounce to sign-in, not render the page. Login redirect: both the email/password flow and Google sign-in now land on /team after a successful login, replacing the previous /dashboard default. Sign-up's post-registration flow is untouched (still routes to /auth/signin?verification=sent, since new accounts require email verification before first login). Team member data (name/role/blurb) is currently hardcoded in features/team/data/team-members.ts, not pulled from Firestore — confirm with BA/PM whether this should stay static or become dynamic later. Three of five members have no blurb in the design mockup — card layout omits the blurb block cleanly when absent, worth a visual check that it still looks balanced.
k1sM2b4HCku0SLHAWR--iMgANBde | [BOOTSTRAP RESTYLING] - Deploy - 120 | Done |  | Not started | Medium | Khanh Nguyen | Daniel Francisco | 2026-08-05 |  |  |  | false |  |  | 4/4 | Live URL loads without errors;Document updated;Deployment completed via boilerplate pipeline;Login → redirect → team page flow spot-checked on the deployed URL | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Update Doc Handoff Done: Deployed the updated application (restyled login page, team page, post-login redirect) to production via Vercel. Verified the live deployment: Sign-in page renders the approved dark gradient + New Rocker styling correctly in production Successful login redirects to /team, not /dashboard Team page displays member cards correctly (name, role badge, blurb) /team is properly protected — visiting it directly while logged out redirects to sign-in, confirmed on the live URL, not just locally Firestore security rules were already deployed to the project via npx firebase-tools deploy --only firestore:rules prior to this task, so no rules changes were needed as part of this deploy. Deliverable: Live production URL: https://group35-team-page-frontend.vercel.app/ Note for next role — Dev 2: Deployment path used: Vercel's GitHub integration, auto-deploying from main on every push — no manual deploy step required going forward. Any future merge to main ships to production immediately with no approval gate on Vercel's side, so treat merging as shipping. If you add new NEXT_PUBLIC_* env vars later, they need to be added manually in Vercel's Project Settings → Environment Variables — existing deployments don't auto-pick them up, and you'll need to trigger a redeploy after adding them. The deploy.yml GitHub Actions workflow (Firestore rules) and Vercel's deploy are two independent pipelines — a change to firebase/firestore.rules won't go live until either that workflow runs on push to main, or someone runs the manual CLI command. Backend (backend/ Express API / Cloud Functions) is not deployed — it requires the Firebase project to be on the paid Blaze plan, and deployment there is manual-only (workflow_dispatch in Actions), not part of this task's scope.
p_RiSqmuLUKf9R_oOafcPcgAC8Rb | [BOOTSTRAP RESTYLING] Test Login → Redirect → Team Page Flow : 60 | Done |  | Not started | Medium | Aindrila Das Prapti | Daniel Francisco | 2026-08-05 |  |  |  | false |  |  | 4/4 | Redirect to team page confirmed;Document updated;All required content verified correct and complete;Valid login tested end-to-end on deployed URL | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document Handoff Done: Completed login-flow testing, authentication checks, team-page content verification, and edge-case testing. Deliverable: https://github.com/khanhngu-git/Group35-Team_Page/pull/11 Note for next role: All assigned tests passed. Testing results are documented in docs/TESTING.md and are ready for PM review/sign-off.
15jNnzJPfkqoF0r0QPqPIcgADl91 | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | Done |  | Not started | Medium | Aindrila Das Prapti | Daniel Francisco | 2026-08-05 |  |  |  | false |  |  | 5/5 | Update Document;Direct team-page access without login tested (must redirect);Bugs logged with repro steps, or none-found confirmed;Missing-photo and long-blurb edge cases tested;Invalid login tested | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Update Doc Handoff Done: Completed edge-case testing for invalid login, direct team-page access without login, missing-photo handling, and unusually long blurb behaviour. Deliverable: Test/login and team by dasaindrila06-debug · Pull Request #11 · khanhngu-git/Group35-Team_Page · GitHub Note for next role: PM - All assigned edge-case tests passed and the results are documented in docs/TESTING.md. The pull request is ready for review and PM sign-off.
icepDIwcV0ugd_zNfMqKp8gANSth | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | Done |  | Not started | Medium | Daniel Francisco | Daniel Francisco | 2026-08-05 |  |  |  | false |  |  | 3/3 | All prior tasks' checklists verified complete;Task moved to Done;Feature reviewed end-to-end against requirements and design | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Document is finalized ande signed off ------ Done: Reviewed all four prior tasks — deployment, edge case testing, login/redirect/team page flow, and design validation — all confirmed complete and meeting requirements. Feature reviewed end-to-end and formally signed off. Deliverable: Final Review & Sign-Off (Left Sign-off comment on everyones tasks) Note for next role: All Sprint 1 bootstrap restyling tasks are complete and signed off. Ready to move to Done.

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
Oai6-Uzh6k2ssL1x7S9GI8gAHFOF | Labels | e_3Emd8x70yJjTxfjDLjBcgAAd8S |  | Not started | Medium |  | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-05 |  |  |  | false
qbWVqfVFrkGZG8TFCaffNMgAFeMq | [BOOTSTRAP RESTYLING] -Write requirements for team page + login styling : 60 | AnxN2eS0B02Grvf5wKcPxcgADTgr |  | In progress | Important | 928abb5a-2601-48bf-b1af-91603c318aa1 | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-05 |  |  |  | false |  |  | 5/5 | Document updated;Edge cases documented;Requirements shared with PM and UX;Team page fields listed with validation/display rules;Login scope explicitly stated as styling-only | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Update Everything on Login Restyling.docx --- Handoff note: Done: Wrote requirements for team page + login styling, including field list, scope statement, and edge cases. Deliverable:Login Restyling & Team Page Requirements Note for next role: Login is styling-only, no new/removed form fields. Team page needs 4 fields per member (name, role, photo, blurb), card-grid layout, ordered by role (PM, BA, UX, Dev). See edge cases in doc for missing photo/long blurb handling.
GilR9Pn-8EGkO9eWWTHBfsgALIXl | [BOOTSTRAP RESTYLING] Design Login Style & Team Page Layout :120 | AnxN2eS0B02Grvf5wKcPxcgADTgr |  | In progress | Medium | 397176ef-7d09-4f5e-b254-b71c0373400c | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-05 |  |  |  | false |  |  | 5/5 | Visual consistency between the two checked;Login page mockup complete;Team page mockup complete;Document Updated;Design shared with BA for validation | UX;Sprint 1 | Produce a mockup/wireframe of the restyled login page and a separate mockup of the team page layout, based on the BA's requirements document. Both must be visually consistent with each other. Update Task documentTask2 (1).pdf Figma Linkhttps://www.figma.com/design/fCinxYwnsMcmcQr3c8K30E/Task2?node-id=25-18&t=eDskqq9RXL0Hc3SS-1 Handoff Done: Produced mockups for restyled login page and new team page, based on BA's requirements document. Confirmed login changes are styling only, no auth logic/field/validation changes. Deliverable: PDF file and Figma link with both mockups, visually consistent card/typography styling across login and team pages. Note for next role - BA: In the Figma link there are annotations made for Typography Styling used and Design choices.
BSmGlUxyEk6KCU8LM_9qQcgACef2 | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | AnxN2eS0B02Grvf5wKcPxcgADTgr |  | Not started | Medium | 928abb5a-2601-48bf-b1af-91603c318aa1 | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-05 |  |  |  | false |  |  | 5/5 | Every required field checked against the design;Login scope confirmed unchanged;Gaps (if any) sent back to UX and resolved;Document Updated;Design formally approved | BA;Sprint 1 | Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Update Document.docx --- Done: Reviewed Ryan's UX mockups (login + team page) against the requirements doc. Confirmed all fields present, login scope stayed styling-only, and edge cases (missing blurb, blurb truncation, missing photo) are handled in the design. Followed up with Ryan on the responsive grid reflow that the design will be implemented in the development phase. Design formally approved. Deliverable: Validate Design AgainstRequirements Note for next role: all requirements have been checked against the design and confirmed. Devs are good to proceed.
fbnP6_HU_UW3IQlkhWqaJcgAIyu7 | [BOOTSTRAP RESTYLING]- Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | AnxN2eS0B02Grvf5wKcPxcgADTgr |  | Not started | Medium | dfcfaaf8-6e09-4935-9f7e-1805b452e159 | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-05 |  |  |  | false |  |  | 4/4 | No authentication logic changed;Visual style matches approved mockup;Update document;Existing login validation/errors still function as before | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. update Document.docx commit: https://github.com/khanhngu-git/Group35-Team_Page/commit/fa8df233d6bf8452de1dbe9b3cbb1d77db26d943 Handoff Done: Implemented the restyled login page based on UX's approved mockups (Task2-UX.pdf). Font, background gradient, card styling, centered labels, and error banner now match the design. Confirmed changes are styling-only — no auth logic, validation, or session handling was modified, aside from one small addition noted below. Deliverable: feature/login-page branch, PR open into main on Group35-Team_Page. Note for next role — Dev (testing): Sign-up page still uses the old (unstyled) light-mode layout, so it'll look inconsistent next to the restyled sign-in page until a follow-up pass is done. Google sign-in button state (grayed out, "Signing in…") only triggers during email/password submission currently, not during the Google OAuth flow itself — worth confirming if that's intended.
MuQZJlZRuUqGXgw7xKmIvMgANTzH | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | AnxN2eS0B02Grvf5wKcPxcgADTgr |  | Not started | Medium | dfcfaaf8-6e09-4935-9f7e-1805b452e159 | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-05 |  |  |  | false |  |  | 4/4 | Team page renders per design with all required fields;Document updated;Team page not directly accessible without login;Successful login redirects to team page | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Update Doc commit: https://github.com/khanhngu-git/Group35-Team_Page/commit/e1239dcbb01b3bec61e6dc793e7d0e511e23b5b7Handoff Done: Built the Team page per the approved design — each member card shows name, role badge, and blurb (where provided). Added "Team" to the sidebar navigation. Wired successful login (both email/password and Google sign-in) to redirect the user to /team. Confirmed the page is unreachable without a valid session. Deliverable: feature/team-page branch, PR open into main on Group35-Team_Page. Note for next role — Dev (testing): Route protection: /team lives inside the (dashboard) route group, so it inherits the same server-side session check as /dashboard, /profile, /settings (redirects to /auth/signin if no session) — also added to proxy.ts's PROTECTED_ROUTES for the edge-level check. Please verify directly: visiting /team while logged out (or with an expired/cleared session cookie) should bounce to sign-in, not render the page. Login redirect: both the email/password flow and Google sign-in now land on /team after a successful login, replacing the previous /dashboard default. Sign-up's post-registration flow is untouched (still routes to /auth/signin?verification=sent, since new accounts require email verification before first login). Team member data (name/role/blurb) is currently hardcoded in features/team/data/team-members.ts, not pulled from Firestore — confirm with BA/PM whether this should stay static or become dynamic later. Three of five members have no blurb in the design mockup — card layout omits the blurb block cleanly when absent, worth a visual check that it still looks balanced.
k1sM2b4HCku0SLHAWR--iMgANBde | [BOOTSTRAP RESTYLING] - Deploy - 120 | AnxN2eS0B02Grvf5wKcPxcgADTgr |  | Not started | Medium | dfcfaaf8-6e09-4935-9f7e-1805b452e159 | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-05 |  |  |  | false |  |  | 4/4 | Live URL loads without errors;Document updated;Deployment completed via boilerplate pipeline;Login → redirect → team page flow spot-checked on the deployed URL | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Update Doc Handoff Done: Deployed the updated application (restyled login page, team page, post-login redirect) to production via Vercel. Verified the live deployment: Sign-in page renders the approved dark gradient + New Rocker styling correctly in production Successful login redirects to /team, not /dashboard Team page displays member cards correctly (name, role badge, blurb) /team is properly protected — visiting it directly while logged out redirects to sign-in, confirmed on the live URL, not just locally Firestore security rules were already deployed to the project via npx firebase-tools deploy --only firestore:rules prior to this task, so no rules changes were needed as part of this deploy. Deliverable: Live production URL: https://group35-team-page-frontend.vercel.app/ Note for next role — Dev 2: Deployment path used: Vercel's GitHub integration, auto-deploying from main on every push — no manual deploy step required going forward. Any future merge to main ships to production immediately with no approval gate on Vercel's side, so treat merging as shipping. If you add new NEXT_PUBLIC_* env vars later, they need to be added manually in Vercel's Project Settings → Environment Variables — existing deployments don't auto-pick them up, and you'll need to trigger a redeploy after adding them. The deploy.yml GitHub Actions workflow (Firestore rules) and Vercel's deploy are two independent pipelines — a change to firebase/firestore.rules won't go live until either that workflow runs on push to main, or someone runs the manual CLI command. Backend (backend/ Express API / Cloud Functions) is not deployed — it requires the Firebase project to be on the paid Blaze plan, and deployment there is manual-only (workflow_dispatch in Actions), not part of this task's scope.
p_RiSqmuLUKf9R_oOafcPcgAC8Rb | [BOOTSTRAP RESTYLING] Test Login → Redirect → Team Page Flow : 60 | AnxN2eS0B02Grvf5wKcPxcgADTgr |  | Not started | Medium | abe831df-57e4-4935-95e5-9210db39f060 | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-05 |  |  |  | false |  |  | 4/4 | Redirect to team page confirmed;Document updated;All required content verified correct and complete;Valid login tested end-to-end on deployed URL | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document Handoff Done: Completed login-flow testing, authentication checks, team-page content verification, and edge-case testing. Deliverable: https://github.com/khanhngu-git/Group35-Team_Page/pull/11 Note for next role: All assigned tests passed. Testing results are documented in docs/TESTING.md and are ready for PM review/sign-off.
15jNnzJPfkqoF0r0QPqPIcgADl91 | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | AnxN2eS0B02Grvf5wKcPxcgADTgr |  | Not started | Medium | abe831df-57e4-4935-95e5-9210db39f060 | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-05 |  |  |  | false |  |  | 5/5 | Update Document;Direct team-page access without login tested (must redirect);Bugs logged with repro steps, or none-found confirmed;Missing-photo and long-blurb edge cases tested;Invalid login tested | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Update Doc Handoff Done: Completed edge-case testing for invalid login, direct team-page access without login, missing-photo handling, and unusually long blurb behaviour. Deliverable: Test/login and team by dasaindrila06-debug · Pull Request #11 · khanhngu-git/Group35-Team_Page · GitHub Note for next role: PM - All assigned edge-case tests passed and the results are documented in docs/TESTING.md. The pull request is ready for review and PM sign-off.
icepDIwcV0ugd_zNfMqKp8gANSth | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | AnxN2eS0B02Grvf5wKcPxcgADTgr |  | Not started | Medium | 63f343eb-a001-41f8-90bd-1b348ac2751e | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-05 |  |  |  | false |  |  | 3/3 | All prior tasks' checklists verified complete;Task moved to Done;Feature reviewed end-to-end against requirements and design | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Document is finalized ande signed off ------ Done: Reviewed all four prior tasks — deployment, edge case testing, login/redirect/team page flow, and design validation — all confirmed complete and meeting requirements. Feature reviewed end-to-end and formally signed off. Deliverable: Final Review & Sign-Off (Left Sign-off comment on everyones tasks) Note for next role: All Sprint 1 bootstrap restyling tasks are complete and signed off. Ready to move to Done.

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
xzWgn1Jo2UCULianDaXw1MgAJAOb | Blocked
e_3Emd8x70yJjTxfjDLjBcgAAd8S | Documents & Updates
a_eQhEo4QEy8wUrcfktg3MgAAmib | Backlog
4hTLJfvxK0inRHAutfYf-MgALA4v | Doing
xu9mw4tE5UqtokiVupeLmsgAE0I2 | Reviewing
cYd0dxg9IUGZeGM9DguwAcgAPoZm | Testing
AnxN2eS0B02Grvf5wKcPxcgADTgr | Done
08e0v0Ie8UOXtuZjnZcalcgAPMZP | Clean up

## Users
User ID | User Name | Email
63f343eb-a001-41f8-90bd-1b348ac2751e | Daniel Francisco | S4036446@student.rmit.edu.au
928abb5a-2601-48bf-b1af-91603c318aa1 | Wen Bin Liang | S4146749@student.rmit.edu.au
397176ef-7d09-4f5e-b254-b71c0373400c | Ryan Lim | S3899858@student.rmit.edu.au
dfcfaaf8-6e09-4935-9f7e-1805b452e159 | Khanh Nguyen | S4090097@student.rmit.edu.au
abe831df-57e4-4935-95e5-9210db39f060 | Aindrila Das Prapti | S4120654@student.rmit.edu.au