## Plan
Plan ID | Plan name | Date of export
GtfNu61PQ0Oo3AQL43j7k8gAFC2N | Week 5 - AI Travel Assistant - Team 35 ¦ A | 2026-08-16

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
iJuFIdxUGkCOU9oksktncMgAEPsm | Labels | Documents & Updates |  | Not started | Medium |  | Daniel Francisco | 2026-08-16 |  |  |  | false
WQnehi1GXUKppUcK9OAElsgAAT3i | Instructions | Documents & Updates |  | Not started | Medium |  | Daniel Francisco | 2026-08-16 |  |  |  | false | [5 empty] | Assign your roles Before touching anything, agree as a team who is PM, BA, UX, Dev 1, and Dev 2. Assign each task on the board to the real person doing it. If your team has fewer than five people, roles can combine. PM Creates the tasks After discussing with the reast of the team, the PM Creates the high level tasks with the description and agrees with the rest of the team on the requirements and the time it requires. You can use many techniques to estimate how long the tasks will take, assume junior level experience. For example creating a set of API end points will take 30 minutes, but a person with no knowledge may require 2 hours. This task still only counts for 30 minutes. Every student can spend up to 10 hours on the project, if a student does not know how to complete the task, this will require them to spend their own remaining time (this means that the real budget is 10 hours not 4). Planning poker can be a good way to make an estimate. (7) Planning Poker Estimation in Scrum: A Guide to Accurate Time Estimation ¦ LinkedIn Update every task as you go Move the card into your column only when you're actually starting it. Don't work ahead. Tick off each item in the Acceptance Criteria checklist as you genuinely complete it — not before. Add a completion comment before moving the card forward: what you did, where the deliverable lives, and anything the next person needs to know. Do this in the card's Notes field — chat/tagging is fine for ongoing discussion, but the handoff itself must be left in the notes. Move the card into the next bucket immediately once it's done. The board should always reflect reality, not what you'll update "later." Handoff structure Once completed make sure to add a note in the notes with your handoff Done: one line on what you actually completed. Deliverable: a link to where it lives (doc, design file, branch/commit, deployed URL). Note for next role: anything the next person needs to know before they start — assumptions you made, edge cases you handled, things you left out of scope. Follow the hard rules — no exceptions No task starts until it's in your column, or it has been assigned to you. Every completion gets a comment before the card moves. Developers never test their own code — Dev 1 builds, Dev 2 tests. The PM writes the cards and signs off last; nobody else marks a task Done.
PO2pYZAqRky_IeDW8P59yMgAPT_d | [DESIGN & BOOTSTRAP] - Stand up web server and database : 180 | Backlog |  | Not started | Medium |  | Daniel Francisco | 2026-08-16 |  |  |  | false |  |  | 0/3 | Confirmed working via a test sign-up;Firebase project created;Authentication and Firestone enabled | DEV;Sprint 1 | Description: Set up the team's Firebase project for the real client build (separate from the mock sprint), enabling Authentication and Firestore. Deliverable: Live Firebase project, confirmed reachable, with Auth and Firestore enabled.
gqN-Lyx4XUuoe3sg8iRlYMgAPK6e | [DESIGN & BOOTSTRAP] - Draft initial requirements from client discussion : 240 | Backlog |  | Not started | Medium |  | Daniel Francisco | 2026-08-16 |  |  |  | false |  |  | 0/3 | Candidate main feature (QR scan flow) identified;Shared with client for confirmation;Problem and target users documented | BA;Sprint 1 | Description: Turn the kick-off call discussion into a written requirements document covering the problem, target users, and the QR scan feature Sprint 2 will build. Deliverable: Requirements document shared with the team.
konbqpRXy0i6ylXRyyUyccgAMunN | [DESIGN & BOOTSTRAP] - Wireframe the QR scan flow : 240 | Backlog |  | Not started | Medium |  | Daniel Francisco | 2026-08-16 |  |  |  | false |  |  | 0/3 | Results display sketched;Shared with BA/PM for feedback;Scan screen sketched | UX;Sprint 1 | Description: Sketch the core screens for the QR scan flow — staff scan screen, results display, and error states. Deliverable: Low-fidelity wireframes for the QR scan flow.
50Fot-TAXE6-0De5O6t33sgAK12F | [DESIGN & BOOTSTRAP] - Client status update & agenda for follow-up : 240 | Backlog |  | Not started | Medium |  | Daniel Francisco | 2026-08-16 |  |  |  | false |  |  | 0/3 | Team aligned on Sprint 1 priorities;Status update sent to client;Follow-up meeting confirmed if needed | PM;Sprint 1 | Description: Summarize the kick-off call outcomes, confirm next steps with the client, and set the agenda for a Week 2 follow-up if needed. Deliverable: Client status update sent, follow-up scheduled if required.
wPMZnV4mmkWgtbNx2Dx9msgAJlLV | [DESIGN & BOOTSTRAP] - Research wheelchair/aircraft door data standards : 240 | Backlog |  | Not started | Medium |  | Daniel Francisco | 2026-08-16 |  |  |  | false |  |  | 0/3 | Relevant standards identified;Findings documented;Shared with Dev team before schema design | DEV;Sprint 1 | Description: Investigate existing standards or data formats for wheelchair dimensions, battery capacity, and aircraft door compatibility (e.g. IATA guidelines) to inform the database schema. Deliverable: Short findings summary shared with the team.

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
iJuFIdxUGkCOU9oksktncMgAEPsm | Labels | bSL-9XRC902PbJQSxFUIp8gAMS7p |  | Not started | Medium |  | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-16 |  |  |  | false
WQnehi1GXUKppUcK9OAElsgAAT3i | Instructions | bSL-9XRC902PbJQSxFUIp8gAMS7p |  | Not started | Medium |  | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-16 |  |  |  | false | [5 empty] | Assign your roles Before touching anything, agree as a team who is PM, BA, UX, Dev 1, and Dev 2. Assign each task on the board to the real person doing it. If your team has fewer than five people, roles can combine. PM Creates the tasks After discussing with the reast of the team, the PM Creates the high level tasks with the description and agrees with the rest of the team on the requirements and the time it requires. You can use many techniques to estimate how long the tasks will take, assume junior level experience. For example creating a set of API end points will take 30 minutes, but a person with no knowledge may require 2 hours. This task still only counts for 30 minutes. Every student can spend up to 10 hours on the project, if a student does not know how to complete the task, this will require them to spend their own remaining time (this means that the real budget is 10 hours not 4). Planning poker can be a good way to make an estimate. (7) Planning Poker Estimation in Scrum: A Guide to Accurate Time Estimation ¦ LinkedIn Update every task as you go Move the card into your column only when you're actually starting it. Don't work ahead. Tick off each item in the Acceptance Criteria checklist as you genuinely complete it — not before. Add a completion comment before moving the card forward: what you did, where the deliverable lives, and anything the next person needs to know. Do this in the card's Notes field — chat/tagging is fine for ongoing discussion, but the handoff itself must be left in the notes. Move the card into the next bucket immediately once it's done. The board should always reflect reality, not what you'll update "later." Handoff structure Once completed make sure to add a note in the notes with your handoff Done: one line on what you actually completed. Deliverable: a link to where it lives (doc, design file, branch/commit, deployed URL). Note for next role: anything the next person needs to know before they start — assumptions you made, edge cases you handled, things you left out of scope. Follow the hard rules — no exceptions No task starts until it's in your column, or it has been assigned to you. Every completion gets a comment before the card moves. Developers never test their own code — Dev 1 builds, Dev 2 tests. The PM writes the cards and signs off last; nobody else marks a task Done.
PO2pYZAqRky_IeDW8P59yMgAPT_d | [DESIGN & BOOTSTRAP] - Stand up web server and database : 180 | 1CJA82g7EEqtGg0qvoBMtsgACqLV |  | Not started | Medium |  | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-16 |  |  |  | false |  |  | 0/3 | Confirmed working via a test sign-up;Firebase project created;Authentication and Firestone enabled | DEV;Sprint 1 | Description: Set up the team's Firebase project for the real client build (separate from the mock sprint), enabling Authentication and Firestore. Deliverable: Live Firebase project, confirmed reachable, with Auth and Firestore enabled.
gqN-Lyx4XUuoe3sg8iRlYMgAPK6e | [DESIGN & BOOTSTRAP] - Draft initial requirements from client discussion : 240 | 1CJA82g7EEqtGg0qvoBMtsgACqLV |  | Not started | Medium |  | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-16 |  |  |  | false |  |  | 0/3 | Candidate main feature (QR scan flow) identified;Shared with client for confirmation;Problem and target users documented | BA;Sprint 1 | Description: Turn the kick-off call discussion into a written requirements document covering the problem, target users, and the QR scan feature Sprint 2 will build. Deliverable: Requirements document shared with the team.
konbqpRXy0i6ylXRyyUyccgAMunN | [DESIGN & BOOTSTRAP] - Wireframe the QR scan flow : 240 | 1CJA82g7EEqtGg0qvoBMtsgACqLV |  | Not started | Medium |  | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-16 |  |  |  | false |  |  | 0/3 | Results display sketched;Shared with BA/PM for feedback;Scan screen sketched | UX;Sprint 1 | Description: Sketch the core screens for the QR scan flow — staff scan screen, results display, and error states. Deliverable: Low-fidelity wireframes for the QR scan flow.
50Fot-TAXE6-0De5O6t33sgAK12F | [DESIGN & BOOTSTRAP] - Client status update & agenda for follow-up : 240 | 1CJA82g7EEqtGg0qvoBMtsgACqLV |  | Not started | Medium |  | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-16 |  |  |  | false |  |  | 0/3 | Team aligned on Sprint 1 priorities;Status update sent to client;Follow-up meeting confirmed if needed | PM;Sprint 1 | Description: Summarize the kick-off call outcomes, confirm next steps with the client, and set the agenda for a Week 2 follow-up if needed. Deliverable: Client status update sent, follow-up scheduled if required.
wPMZnV4mmkWgtbNx2Dx9msgAJlLV | [DESIGN & BOOTSTRAP] - Research wheelchair/aircraft door data standards : 240 | 1CJA82g7EEqtGg0qvoBMtsgACqLV |  | Not started | Medium |  | 63f343eb-a001-41f8-90bd-1b348ac2751e | 2026-08-16 |  |  |  | false |  |  | 0/3 | Relevant standards identified;Findings documented;Shared with Dev team before schema design | DEV;Sprint 1 | Description: Investigate existing standards or data formats for wheelchair dimensions, battery capacity, and aircraft door compatibility (e.g. IATA guidelines) to inform the database schema. Deliverable: Short findings summary shared with the team.

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
b898T002_kyRoYbG-U5-xsgAHWM- | Blocked
bSL-9XRC902PbJQSxFUIp8gAMS7p | Documents & Updates
1CJA82g7EEqtGg0qvoBMtsgACqLV | Backlog
hiLxLyiFh0SJPzpfvaDgkcgAMLtF | Doing
waVpHF6yrEqrdddQnL5-McgAD2Yj | Testing (if required)
lXyAa8ofvUu2KnVIu526s8gAG16P | Reviewing
5DuGraFeBkWOmAM9QUXcHsgAC9sT | Done
7Ol1XHtiYUevfQQyikua6cgAAZi5 | Clean up

## Users
User ID | User Name | Email
63f343eb-a001-41f8-90bd-1b348ac2751e | Daniel Francisco | S4036446@student.rmit.edu.au